## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | Date Added | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
As a developer, I want to be able to create new API paths | 6 | 2020-01-27
create directory |  |  | Dumitru | COMPLETE | 1 | 0 | 0 | 0 | 0 | 0 | 0
initialise required libaries and middle ware |  |  | Dumitru | COMPLETE | 1 | 0 | 0 | 0 | 0 | 0 | 0
connect to database |  |  | Dumitru | COMPLETE | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0
As a developer, I want to be able to create a parser to parse the csv file into the database | 5 | 2020-01-27
read in file |  |  | John | COMPLETE | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
feed into database and in correct format |  |  | John | COMPLETE | 4 | 0 | 0 | 0 | 0 | 0 | 0
As a developer, I want to calculate the distance from the user to the provider | 5 | 2020-01-29
get location from user |  |  | Dumitru, Ross,John | COMPLETE | 6 | 6 | 6 | 0 | 0 | 0 | 0
get location of hospitals |  |  | Dumitru, Ross,John | COMPLETE | 3 | 3 | 3 | 3 | 0 | 0 | 0
calculate distance |  |  | Dumitru, Ross,John | COMPLETE | 5 | 5 | 5 | 5 | 2.5 | 0 | 0
display to user |  |  | Sophie, Dominika | COMPLETE | 3 | 3 | 3 | 3 | 3 | 0 | 0
As a developer, I want to have a database to store the dataset in | 5 | 2020-01-27
create database |  |  | Patrick | COMPLETE | 1.5 | 0 | 0 | 0 | 0 | 0 | 0
create appropriate tables and relationships |  |  | Patrick | COMPLETE | 3 | 0 | 0 | 0 | 0 | 0 | 0
populate database |  |  | Patrick, John | COMPLETE | 6 | 6 | 0 | 0 | 0 | 0 | 0
create basic procedures |  |  | Patrick | COMPLETE | 4 | 4 | 2 | 0 | 0 | 0 | 0
As a developer, I want to be able to create a responsive website | 3 | 2020-01-27
create framework in html |  |  | Sophie, Dominika | COMPLETE | 4 | 2 | 0 | 0 | 0 | 0 | 0
add CSS |  |  | Sophie, Dominika | COMPLETE | 4 | 2 | 1 | 0 | 0 | 0 | 0
As an application user, I want to be able to search for my treatment | 3 | 2020-01-27
create sql procedure |  |  | Patrick | COMPLETE | 1 | 0 | 0 | 0 | 0 | 0 | 0
create front end to take input |  |  | Sophie, Dominika | COMPLETE | 2 | 2 | 2 | 0 | 0 | 0 | 0
create javascript to take input and search for it in the database |  |  | Dumitru, Ross, John | COMPLETE | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0
display result to user |  |  | Sophie, Dominika | COMPLETE | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0
As an application user, I want to be able to view my results on a map | 3 | 2020-01-27
research |  |  | Sophie, Dominika | COMPLETE | 4 | 0 | 0 | 0 | 0 | 0 | 0
connect to map api |  |  | Sophie, Dominika | COMPLETE | 3 | 3 | 0 | 0 | 0 | 0 | 0
display map on front end |  |  | Sophie, Dominika | COMPLETE | 6 | 6 | 6 | 1 | 0 | 0 | 0
display markers of hospitals |  |  | Sophie, Dominika | ON TRACK | 4 | 4 | 4 | 4 | 2 | 1 | 0
As an application user, I want to share live location | 4 | 2020-01-27
connect to map api |  |  | Sophie, Dominika | COMPLETE | 1 | 1 | 0 | 0 | 0 | 0 | 0
get live location |  |  | Sophie, Dominika | COMPLETE | 3 | 3 | 0.5 | 0 | 0 | 0 | 0
display on map |  |  | Sophie, Dominika | ON TRACK | 2 | 2 | 1 | 1 | 0.5 | 0.5 | 0
TOTAL |  |  |  |  | 77.5 | 56.5 | 35 | 17 | 8 | 1.5 | 0
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.