## Sheet1
Product Backlog
User Story Title | Description | Priority (1 low, 10 high) | Estimate | Notes | Tests | Date Added
API | As a developer, I want to be able to create new API paths | 10 | 6 |  | Test developer can just create new API paths | 2020-01-23
Parser | As a developer, I want to be able to create a parser to parse the csv file into the database | 10 | 5 |  | Test that developer will be able to parse, process and input the csv dataset into the database. | 2020-01-23
Distance Calculator | As a developer, I want to calculate the distance from the user to the provider | 10 | 5 |  |  | 2020-01-23
Create database | As a developer, I want to have a database to store the dataset in | 10 | 5 | Create required schema, tables, queries and procedures |  | 2020-01-23
Create website | As a developer, I want to be able to create a responsive website | 10 | 3 | Website skeleton, search functionality |  | 2020-01-23
Search for treatment | As an application user, I want to be able to search for my treatment | 9 | 3 | Support search by condition and procedure | 1.Test that a real treatment is shown in the results 2. Test that a fake treatment generates an error message | 2020-01-22
View results on a map (Map Integration) | As an application user, I want to be able to view my results on a map | 8 | 4 |  | Test that map displayed with correct results | 2020-01-22
Set live location | As an application user, I want to share live location | 8 | 4 |  | Test that live location is accurate | 2020-01-22
Set constraint based on location | As an application user, I want to be able to set a constraint based on my set location so I can find hospitals close to me | 7 | 2 |  | Test that results that fit the constraints based on set location are displayed | 2020-01-22
Set constraint based on set price range | As an application user, I want to be able to set a constraint based on my set price range so I can find treatment in my price range | 7 | 2 |  | Test that results that fit the constraints based on set price range are displayed | 2020-01-22
Order results based on price | As an application user, I want to be able to order the results based on price so I can so the cheapest or most expensive in order | 7 | 1 |  | Test that results search are ordered from lowest to highest | 2020-01-22
Order results based on distance | As an application user, I want to be able to order the results based on distance from my location so I can find the closest to myself | 7 | 1 |  | Test that search results are ordered from closest to either live location or manual location, to furthest away | 2020-01-22
Set location manually | As an application user, I want to set my location manually so I can see result based on somewhere I may be in the future | 6 | 2 |  | Test that location can be entered by user and search matches location | 2020-01-22
Order results based on custom ranking of price, distance and user feedback | As an application user, I want to be able to order the results based on my price, distance and user feedback constraints so I can see what others thought of the service | 3 | 4 | Get more info (on cust. feedback) from the client at meeting Friday 31st Jan | Test that search parameters can be entered, and the correct results are displayed | 2020-01-22
Load new/edited data to update existing data set | As a user, I want to be able to load new/edited data to update the data set so I can keep the data up-to-date | 1 | 5 |  | Test that data can be updated in the data set, and have the frontend display data accordingly | 2020-01-22
Load new/ edited data to add to existing data set | As a user, I want to be able to load new/edited data to add to the existing data set | 1 | 5 |  | Test that data is loaded without errors | 2020-01-22
Load new/ edited data to delete from existing data set | As a user, I want to be able to load new/edited data to delete from existing data set so I can keep the data up-to-date | 1 | 5 |  | Test that data can be deleted from data set | 2020-01-22