## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | Date Added | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
As a application user, I want to be ale to set a constraint based on my set location | 2 | 2020-02-03
0
0
0
As an application user, I want to be ale to set a constraint based on my set price range. | 2 | 2020-02-03
0
0
As an application user, I want to be able to order my results based on price. | 1 | 2020-02-03
0
0
0
0
As an pplcation user, I want to be able to order the results based on distance from my location | 1 | 2020-02-03
0
0
0
0
As an application user, I want to set my location manually | 2 | 2020-02-03
0
0
As an application user, I want to be able to order the results based on my price, distance and user feedback constraints | 4 | 2020-02-03
0
0
0
0
As a user, I want to be able to load new/editited data to update the data set | 5 | 2020-02-03
0
0
As a user, I want to be able to load new/editied data to add to the existing data set | 5 | 2020-02-03
0
0
As a user, I want to be able to load new/edited data to delete from existing data set | 5 | 2020-02-03
0
0
TOTAL |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.