## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | Date Added | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
As a application user, I want to be able to set a constraint based on my set location | 2 | 2020-02-03 |  | Incomplete
have ability to set location on front end |  |  | Sophie, Dominika | Incomplete | 2 | 0 | 0 | 0 | 0 | 0 | 0
create front end element to give the user abilitly to set constraint |  |  | Sophie, Dominika | Incomplete | 2 | 0 | 0 | 0 | 0 | 0 | 0
create stored procedure |  |  | Patrick | Incomplete | 1 | 0 | 0 | 0 | 0 | 0 | 0
create back end javascript to connect the front end and the database |  |  | John, Ross, Dumitru | Incomplete | 3 | 0 | 0 | 0 | 0 | 0 | 0
As an application user, I want to be able to set a constraint based on my set price range. | 2 | 2020-02-03 |  | Incomplete
create front end element to give the user abilitly to set constraint |  |  | Sophie, Dominika | Incomplete | 2 | 0 | 0 | 0 | 0 | 0 | 0
create stored procedure |  |  | Patrick | Incomplete | 1 | 0 | 0 | 0 | 0 | 0 | 0
create back end javascript to connect the front end and the database |  |  | John, Ross, Dumitru | Incomplete | 3 | 0 | 0 | 0 | 0 | 0 | 0
As an application user, I want to be able to order my results based on price. | 1 | 2020-02-03 |  | Incomplete
create front end element to give the user abilitly to order results |  |  | Sophie, Dominika | Incomplete | 2 | 0 | 0 | 0 | 0 | 0 | 0
create stored procedure |  |  | Patrick | Incomplete | 1 | 0 | 0 | 0 | 0 | 0 | 0
create back end javascript to connect the front end and the database |  |  | John, Ross, Dumitru | Incomplete | 3 | 0 | 0 | 0 | 0 | 0 | 0
As an pplcation user, I want to be able to order the results based on distance from my location | 1 | 2020-02-03 |  | Incomplete
have ability to set location on front end |  |  | Sophie, Dominika | Incomplete | 2 | 0 | 0 | 0 | 0 | 0 | 0
create front end element to give the user abilitly to order results |  |  | Sophie, Dominika | Incomplete | 2 | 0 | 0 | 0 | 0 | 0 | 0
create stored procedure |  |  | Patrick | Incomplete | 1 | 0 | 0 | 0 | 0 | 0 | 0
create back end javascript to connect the front end and the database |  |  | John, Ross, Dumitru | Incomplete | 3 | 0 | 0 | 0 | 0 | 0 | 0
As an application user, I want to set my location manually | 2 | 2020-02-03 |  | Incomplete
have ability for user to select desired location |  |  | Sophie, Dominika | Incomplete | 3 | 0 | 0 | 0 | 0 | 0 | 0
display on map |  |  | Sophie, Dominika | Incomplete | 2 | 0 | 0 | 0 | 0 | 0 | 0
As an application user, I want to be able to order the results based on my price, distance and user feedback constraints | 4 | 2020-02-03 |  | Incomplete
set weighting of price, distance and user feedback |  |  | Patrick | Incomplete | 2 | 0 | 0 | 0 | 0 | 0 | 0
create front end element to give the user abilitly to order results |  |  | Sophie, Dominika | Incomplete | 2 | 0 | 0 | 0 | 0 | 0 | 0
create stored procedure |  |  | Patrick | Incomplete | 1 | 0 | 0 | 0 | 0 | 0 | 0
create back end javascript to connect the front end and the database |  |  | John, Ross, Dumitru | Incomplete | 3 | 0 | 0 | 0 | 0 | 0 | 0
As an admin, I want to be able to load new/editited data to update the data set | 5 | 2020-02-03 |  | Incomplete
create element to allow upload of data |  |  | Sophie, Dominika | Incomplete | 2 | 0 | 0 | 0 | 0 | 0 | 0
create element to view upload of data |  |  | Sophie, Dominika | Incomplete | 2 | 0 | 0 | 0 | 0 | 0 | 0
create stored procedure to add data |  |  | Patrick | Incomplete | 1 | 0 | 0 | 0 | 0 | 0 | 0
create back end javascript to connect the front end and the database |  |  | John, Ross, Dumitru | Incomplete | 3 | 0 | 0 | 0 | 0 | 0 | 0
As an admin, I want to be able to load new/editied data to add to the existing data set | 5 | 2020-02-03 |  | Incomplete
create element to allow upload of data |  |  | Sophie, Dominika | Incomplete | 2 | 0 | 0 | 0 | 0 | 0 | 0
create element to view upload of data |  |  | Sophie, Dominika | Incomplete | 2 | 0 | 0 | 0 | 0 | 0 | 0
create stored procedure to add data |  |  | Patrick | Incomplete | 1 | 0 | 0 | 0 | 0 | 0 | 0
create back end javascript to connect the front end and the database |  |  | John, Ross, Dumitru | Incomplete | 3 | 0 | 0 | 0 | 0 | 0 | 0
As an admin, I want to be able to load new/edited data to delete from existing data set | 5 | 2020-02-03 |  | Incomplete
create element to allow data to be deleted |  |  | Sophie, Dominika | Incomplete | 2 | 0 | 0 | 0 | 0 | 0 | 0
create stored procedure to delete data |  |  | Patrick | Incomplete | 1 | 0 | 0 | 0 | 0 | 0 | 0
create back end javascript to connect the front end and the database |  |  | John, Ross, Dumitru | Incomplete | 3 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  |  |  | 63 | 0 | 0 | 0 | 0 | 0 | 0
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.